## Sheet1
Printed By: Li Shiyun
EXCEL MARCO INDUSTRIAL SYSTEMS PTE. LTD.
Project Sales & Profit Margin Report
2023-03-09 10:40
Financial Year : 2022 Project Status : All
S/N | Project No | Description | Client | Sales Amount (Nature) | Exch Rate | Sales Amount (Home) | Alloc Prj Budget (Home) | Target Gross Profit (Home) | Target Gross Profit (%) | Total PO On Order | Actual Cost Labour | Actual Prj Cost (Home) | Prj Cost Saving (Home) | Actual Gross Profit (Home) | Actual Gross Profit (%) | Project Status | Target Delivery Date | Commencial I/C | Project I/C
1 | A21001 | A21001 - PPL P2045 VMS | PPL Shipyard Pte Ltd | 498,790.00 | 1.000000000 | 498,790.00 | 348,812.07 | 149,977.93 | 0.300684 | 0.00 | 420.00 | 334,211.09 | 14,600.98 | 164,578.91 | 32.995631 | Closed | 30/06/2016 | Bryan Wong | Projects - Win - A001
2 | A21002 | A21002 - PPL P2046 VMS | PPL Shipyard Pte Ltd | 491,990.00 | 1.000000000 | 491,990.00 | 349,781.07 | 142,208.93 | 0.289048 | 0.00 | 676.00 | 331,059.50 | 18,721.57 | 160,930.50 | 32.710116 | Closed | 30/06/2016 | Bryan Wong | Projects - Win - A001
3 | A21003 | A21003 - PPL P2053 VMS | PPL Shipyard Pte Ltd | 503,380.00 | 1.000000000 | 503,380.00 | 341,291.18 | 162,088.82 | 0.322001 | 0.00 | 6,636.00 | 284,210.70 | 57,080.48 | 219,169.30 | 43.539533 | Closed | 30/06/2016 | Tony Tan | Projects - Edward - A002
37 | B21011 | T375A - Hazard Warning System | UG M&E Pte Ltd | 568,000.00 | 1.000000000 | 568,000.00 | 497,683.23 | 70,316.77 | 0.123797 | 0.00 | 65,236.00 | 324,502.96 | 173,180.27 | 243,497.04 | 42.869197 | Run | 28/02/2024 | Edward Aung | Projects - Edward - A004
38 | B21012 | LIZA 2 Topside _ICSS | Single Buoy Moorings Inc. | 3,501,831.82 | 1.351970000 | 4,734,371.55 | 3,724,521.76 | 1,009,849.79 | 0.213302 | 0.00 | 1,056,735.00 | 3,688,329.15 | 36,192.61 | 1,046,042.40 | 22.094641 | Closed | 27/11/2020 | Edward Aung | Projects - Edward - B002
39 | B21013 | FPSO Sepetiba Topsides ICSS (MERO 2) | SBM Offshore Group | 5,772,065.00 | 1.400990000 | 8,086,605.32 | 6,327,735.52 | 1,758,869.80 | 0.217504 | 0.00 | 844,725.00 | 6,027,854.45 | 299,881.07 | 2,058,750.87 | 25.458778 | Run | 18/03/2021 | Edward Aung | Projects - Edward - B002
40 | B21015 | FPSO Prosperity (Topside ICSS) | SBM Offshore Group | 3,370,393.00 | 1.375500000 | 4,635,975.62 | 3,770,343.06 | 865,632.56 | 0.186721 | 0.00 | 703,817.50 | 3,771,200.20 | -857.14 | 864,775.42 | 18.653580 | Run | 28/02/2023 | Kong Swee Suang | SBM - SS Kong
48 | C25001_004 | C25001_004 - Girls College Al Hasa / DMC200-10 / A053U932 PO received | Cummins Power Generation Ltd | 30,581.68 | 1.280000000 | 39,144.54 | 36,241.89 | 2,902.65 | 0.074152 | 0.00 | 0.00 | 36,969.42 | -727.53 | 2,175.12 | 5.556637 | Closed | 31/03/2016 | Tony Tan | Cummins - C100
49 | C25001_005 | C25001_005 - Loose Items for Eunos Switchgear PO received | PT. Tamco Indonesia | 1,236.81 | 1.280000000 | 1,583.12 | 2,438.71 | -855.59 | -0.540445 | 0.00 | 0.00 | 2,460.62 | -21.91 | -877.50 | -55.428521 | Closed | 29/02/2016 | Tony Tan | Cummins - C100
50 | C25001_006 | C25001_006 - LG CNS Busan + Modification Material / DMC200-12 / A054A221 PO received | Cummins Power Generation Ltd | 45,334.68 | 1.280000000 | 58,028.39 | 54,050.21 | 3,978.18 | 0.068556 | 0.00 | 0.00 | 61,470.44 | -7,420.23 | -3,442.05 | -5.931666 | Closed | 29/01/2016 | Tony Tan | Cummins - C100
51 | C25001_007 | C25001_007 PIBT PROJECT | Cummins Power Generation Ltd | 26,676.74 | 1.280000000 | 34,146.23 | 31,654.18 | 2,492.05 | 0.072982 | 0.00 | 1,324.00 | 39,542.86 | -7,888.68 | -5,396.63 | -15.804468 | Closed | 29/04/2016 | Tony Tan | Cummins - C100
562 | D21022 | D21022 Fast4Ward - MPF Nbr.1 Construction | SBM Offshore Group | 4,480.00 | 1.377070000 | 6,169.27 | 3,855.80 | 2,313.47 | 0.374999 | 0.00 | 0.00 | 2,772.00 | 1,083.80 | 3,397.27 | 55.067617 | Closed | 01/01/2020 | Xia BoFeng | Projects - Xia Bofeng - D001
563 | D21023 | D21023 CMHI-220 SBM F4WD MPFA GAS SAMPLING SYSTEM | China Merchants Heavy Industry (Jiangsu) Co., Ltd | 71,700.00 | 1.353990000 | 97,081.08 | 65,397.72 | 31,683.36 | 0.326360 | 0.00 | 0.00 | 59,678.94 | 5,718.78 | 37,402.14 | 38.526704 | Closed | 31/01/2021 | Gu Chengzhuo | Projects - Xia Bofeng - D001
564 | D21024 | D21024 CMHI129-1/2 PAGA SYSTEM MODIFICATION | SELECTIVE MARINE SERVICES Co. (L.L.C.) | 12,600.00 | 1.353990000 | 17,060.27 | 12,862.91 | 4,197.36 | 0.246031 | 0.00 | 0.00 | 4,381.73 | 8,481.18 | 12,678.54 | 74.316174 | Closed | 31/12/2019 | Gu Chengzhuo | Projects - Xia Bofeng - D001
565 | D21025 | D21025 CMHI-129 3&4 CCTV CAMERA | China Merchants Heavy Industry (Shenzhen) Co., Ltd | 40,600.00 | 1.379650000 | 56,013.79 | 29,427.93 | 26,585.86 | 0.474631 | 0.00 | 0.00 | 28,386.41 | 1,041.52 | 27,627.38 | 49.322461 | Closed | 31/07/2020 | Gu Chengzhuo | Projects - Xia Bofeng - D001
603 | IP3009 | In-House Project - Research on potential Innovative Projects | Excel Marco Industrial Systems Pte Ltd | 0.00 | 1.000000000 | 0.00 | 0.00 | 0.00 | 0.000000 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.000000 | Closed | 31/03/2017 | Bryan Wong | P&E In-House Projects
604 | IP3010 | In-House Project - SAT Internal Checklist | Excel Marco Industrial Systems Pte Ltd | 0.00 | 1.000000000 | 0.00 | 0.00 | 0.00 | 0.000000 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.000000 | Closed | 31/03/2017 | Bryan Wong | P&E In-House Projects
605 | IP3011 | In-House Project - FSM Certification | Excel Marco Industrial Systems Pte Ltd | 0.00 | 1.000000000 | 0.00 | 0.00 | 0.00 | 0.000000 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.000000 | Run | 29/12/2017 | Saw Mar Mar | P&E In-House Projects
606 | IP3012 | In-House Project - Joulon Support Services | Excel Marco Industrial Systems Pte Ltd | 0.00 | 1.000000000 | 0.00 | 0.00 | 0.00 | 0.000000 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.000000 | Run | 20/10/2020 | Bryan Wong | P&E In-House Projects
607 | IP3013 | Maintenance Support System | Excel Marco Industrial Systems Pte Ltd | 0.00 | 1.000000000 | 0.00 | 0.00 | 0.00 | 0.000000 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.000000 | Run | 31/12/2018 | Saw Mar Mar | P&E In-House Projects
608 | IP3014 | In-House Project - NRF OpsTrace Assessment Tool and System (IP3502) | Excel Marco Industrial Systems Pte Ltd | 0.00 | 1.000000000 | 0.00 | 145,266.67 | -145,266.67 | 0.000000 | 0.00 | 0.00 | 13,559.47 | 131,707.20 | -13,559.47 | 0.000000 | Closed | 31/12/2019 | Saw Mar Mar | Projects - Win - B001
631 | M27008 | PUB000ETT20300146 Preventive and Corrective Maintenance of SCADA and PLC at Waterworks, Desalinatin Plants, Outstations and Newater | Public Utilities Board | 1,779,750.00 | 1.000000000 | 1,779,750.00 | 1,531,332.43 | 248,417.57 | 0.139580 | 0.00 | 532,656.00 | 1,045,582.29 | 485,750.14 | 734,167.71 | 41.251171 | Run | 30/11/2022 | Huang Guoqing | Projects - Edward - A004
632 | M27009 | SPOX Maintenance Contract | Katoen Natie Singapore (Jurong) Pte Ltd | 28,000.00 | 1.000000000 | 28,000.00 | 15,000.00 | 13,000.00 | 0.464286 | 0.00 | 0.00 | 5,262.55 | 9,737.45 | 22,737.45 | 81.205179 | Closed | 01/02/2022 | Huang Guoqing | Projects - Edward - A004
633 | M27010 | OSX2 AD-HOC SUPPORT | The Masters and Owners OSX 2 Leasing B.V. of M/V OSX 2 | 3,975.00 | 1.000000000 | 3,975.00 | 2,420.00 | 1,555.00 | 0.391195 | 0.00 | 0.00 | 132.00 | 2,288.00 | 3,843.00 | 96.679245 | Closed | 15/10/2021 | Trizel Chong | Projects - Edward - B002
653 | S22018 | Cdm maintenance contract email/telephone | ALFA LULA ALTO HOLDING | 16,700.00 | 1.359700000 | 22,707.00 | 1,162.54 | 21,544.46 | 0.948803 | 0.00 | 0.00 | 1,109.00 | 53.54 | 21,598.00 | 95.116044 | Closed | 13/10/2017 | Saw Mar Mar | Service - Trizel
654 | S22019 | Cdm offshore service | ALFA LULA ALTO HOLDING | 25,480.30 | 1.359700000 | 34,645.56 | 15,008.37 | 19,637.19 | 0.566802 | 0.00 | 0.00 | 15,901.73 | -893.36 | 18,743.83 | 54.101680 | Closed | 30/11/2016 | Chay Foo Cheong | Service - Naing Win Kyaw
655 | S22020 | Turritella spare | SBM Offshore Group | 15,730.00 | 1.000000000 | 15,730.00 | 10,790.00 | 4,940.00 | 0.314050 | 0.00 | 0.00 | 6,863.78 | 3,926.22 | 8,866.22 | 56.365035 | Closed | 30/01/2017 | Chay Foo Cheong | Service - Naing Win Kyaw
656 | S22021 | FPSO Turritella spare | SBM Offshore Group | 19,400.00 | 1.393300000 | 27,030.02 | 14,378.86 | 12,651.16 | 0.468041 | 0.00 | 0.00 | 7,082.73 | 7,296.13 | 19,947.29 | 73.796801 | Closed | 31/01/2017 | Chay Foo Cheong | Service - Naing Win Kyaw
657 | S22022 | FPSO Turritella site support | SBM Stones Operations LLC | 68,307.62 | 1.446200000 | 98,786.48 | 48,583.64 | 50,202.84 | 0.508195 | 0.00 | 35,046.00 | 51,460.84 | -2,877.20 | 47,325.64 | 47.907001 | Closed | 28/02/2017 | Chay Foo Cheong | Service - Naing Win Kyaw
658 | S22023 | FPSO Turritella offshore support | SBM Offshore Group | 35,544.61 | 1.405070000 | 49,942.66 | 31,801.34 | 18,141.32 | 0.363243 | 0.00 | 15,732.00 | 21,996.41 | 9,804.93 | 27,946.25 | 55.956671 | Closed | 28/04/2017 | Chay Foo Cheong | Service - Naing Win Kyaw
659 | S22024 | FPSO Turritella support | SBM Stones Operations LLC | 20,424.10 | 1.405070000 | 28,697.29 | 20,595.52 | 8,101.77 | 0.282318 | 0.00 | 3,744.00 | 10,602.00 | 9,993.52 | 18,095.29 | 63.055745 | Closed | 20/04/2017 | Chay Foo Cheong | Service - Naing Win Kyaw